## Tabelle1
Name | Probability | Damage | Risc factor | Mitigation | Person in Charge
Ineffective communication | 30% | 6 | 1.8 | Talking everything out properly | Robin
Stalled progress in developement | 25% | 7 | 1.75 | More people working on it | Nico S.
Someone drops out | 10% | 10 | 1 | Everyone should be able to do everything | Kevin
No work has been done the whole week | 5% | 10 | 0.5 | Check progress on Tuesday | Robin
Illness | 15% | 4 | 0.6 | Be sure to delegate your tasks | Nico R.